Appendix A, Item 3. Project Timeline with Tasks

| Task | Year 1 (June, 1 2012-May, 30 2013) |
| --- | --- |
|  | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May |
| Intervention Development |  |  |  |  |  |  |  |  |  |  |  |  |
| Pre-development focus group |  |  |  |  |  |  |  |  |  |  |  |  |
| Design Team meets; develops Unit 1 |  |  |  |  |  |  |  |  |  |  |  |  |
| The first brief teaching trial (Unit 1) |  |  |  |  |  |  |  |  |  |  |  |  |
| Revise Unit 1 |  |  |  |  |  |  |  |  |  |  |  |  |
| Develop Unit 2 |  |  |  |  |  |  |  |  |  |  |  |  |
| The second brief teaching trial (Unit 2) |  |  |  |  |  |  |  |  |  |  |  |  |
| Revise Unit 2 |  |  |  |  |  |  |  |  |  |  |  |  |
| Develop Unit 3 |  |  |  |  |  |  |  |  |  |  |  |  |
| The third brief teaching trial (Unit 3) |  |  |  |  |  |  |  |  |  |  |  |  |
| Revise Unit 3 |  |  |  |  |  |  |  |  |  |  |  |  |
| Develop Unit 4 |  |  |  |  |  |  |  |  |  |  |  |  |
| The fourth brief teaching trial (Unit 4) |  |  |  |  |  |  |  |  |  |  |  |  |
| Revise Unit 4 |  |  |  |  |  |  |  |  |  |  |  |  |
| Final revisions to all units |  |  |  |  |  |  |  |  |  |  |  |  |
| Develop Professional Development (PD) |  |  |  |  |  |  |  |  |  |  |  |  |
| Measurement Development |  |  |  |  |  |  |  |  |  |  |  |  |
| Fidelity observation measure |  |  |  |  |  |  |  |  |  |  |  |  |
| Teachers’ science teaching log |  |  |  |  |  |  |  |  |  |  |  |  |
| SPA measure |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Management |  |  |  |  |  |  |  |  |  |  |  |  |
| Hire key personnel |  |  |  |  |  |  |  |  |  |  |  |  |
| Quarterly research meeting |  |  |  |  |  |  |  |  |  |  |  |  |
| Annual leadership team meeting |  |  |  |  |  |  |  |  |  |  |  |  |
| Research Method |  |  |  |  |  |  |  |  |  |  |  |  |
| Recruit focus group teachers/consent (n=10) |  |  |  |  |  |  |  |  |  |  |  |  |
| Recruit teachers for trials/consent (n=16) |  |  |  |  |  |  |  |  |  |  |  |  |
| Recruit teachers for feasibility study in Year 2/consent (n=24) |  |  |  |  |  |  |  |  |  |  |  |  |
| Individual and Focus-group Interview |  |  |  |  |  |  |  |  |  |  |  |  |
| Classroom observation |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Year 2 (June, 1 2013-May, 30 2014) |
|  | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May |
| Intervention Implementation |  |  |  |  |  |  |  |  |  |  |  |  |
| Feasibility study |  |  |  |  |  |  |  |  |  |  |  |  |
| Revise all units and PD |  |  |  |  |  |  |  |  |  |  |  |  |
| Measurement Development |  |  |  |  |  |  |  |  |  |  |  |  |
| Revise fidelity observation measure |  |  |  |  |  |  |  |  |  |  |  |  |
| Revise SPA measure |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Management |  |  |  |  |  |  |  |  |  |  |  |  |
| Quarterly research meeting |  |  |  |  |  |  |  |  |  |  |  |  |
| Annual leadership team meeting |  |  |  |  |  |  |  |  |  |  |  |  |
| Research Method |  |  |  |  |  |  |  |  |  |  |  |  |
| Deliver summer PD |  |  |  |  |  |  |  |  |  |  |  |  |
| Ascertain children for feasibility study (n=144) |  |  |  |  |  |  |  |  |  |  |  |  |
| Individual and Focus-group Interview |  |  |  |  |  |  |  |  |  |  |  |  |
| Classroom observation |  |  |  |  |  |  |  |  |  |  |  |  |
| Collect teacher data |  |  |  |  |  |  |  |  |  |  |  |  |
| Collect child data |  |  |  |  |  |  |  |  |  |  |  |  |
| Data entry/coding |  |  |  |  |  |  |  |  |  |  |  |  |
| Finalize data base for feasibility study |  |  |  |  |  |  |  |  |  |  |  |  |
| Recruit teachers for pilot study/consent (n=30) |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Year 3 (June, 1 2014-May,30 2015) |
|  | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May |
| Intervention Implementation |  |  |  |  |  |  |  |  |  |  |  |  |
| Pilot study |  |  |  |  |  |  |  |  |  |  |  |  |
| Revise all units and PD |  |  |  |  |  |  |  |  |  |  |  |  |
| Finalize intervention |  |  |  |  |  |  |  |  |  |  |  |  |
| Project Management |  |  |  |  |  |  |  |  |  |  |  |  |
| Quarterly research meeting |  |  |  |  |  |  |  |  |  |  |  |  |
| Annual leadership team meeting |  |  |  |  |  |  |  |  |  |  |  |  |
| Research Method |  |  |  |  |  |  |  |  |  |  |  |  |
| Ascertain children for pilot study (n=180) |  |  |  |  |  |  |  |  |  |  |  |  |
| Deliver summer PD |  |  |  |  |  |  |  |  |  |  |  |  |
| Individual and Focus-group Interview |  |  |  |  |  |  |  |  |  |  |  |  |
| Classroom observation |  |  |  |  |  |  |  |  |  |  |  |  |
| Collect teacher data |  |  |  |  |  |  |  |  |  |  |  |  |
| Collect child data |  |  |  |  |  |  |  |  |  |  |  |  |
| Data entry/coding |  |  |  |  |  |  |  |  |  |  |  |  |
| Finalize data base for pilot study |  |  |  |  |  |  |  |  |  |  |  |  |