Table 2. Project timeline with tasks and quarter implemented.

|  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Task** | **Year 1**  9/11-8/12 | | | | **Year 2**  9/12-8/13 | | | | **Year 3**  9/13-8/14 | | | |
|  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 |
| Teacher focus groups |  |  |  |  |  |  |  |  |  |  |  |  |
| Develop intervention and summer PD experience |  |  |  |  |  |  |  |  |  |  |  |  |
| Teaching trials (4 teachers) |  |  |  |  |  |  |  |  |  |  |  |  |
| Recruit 15 teacher participants (Cohort 1) |  |  |  |  |  |  |  |  |  |  |  |  |
| Summer 1 PD experience |  |  |  |  |  |  |  |  |  |  |  |  |
| Teachers implement intervention (before Christmas break) |  |  |  |  |  |  |  |  |  |  |  |  |
| Ongoing PD for teachers |  |  |  |  |  |  |  |  |  |  |  |  |
| Collect and analyze teacher data |  |  |  |  |  |  |  |  |  |  |  |  |
| Collect and analyze student data |  |  |  |  |  |  |  |  |  |  |  |  |
| Revision of PD experience and intervention |  |  |  |  |  |  |  |  |  |  |  |  |
| Recruit 15 teacher participants (Cohort 2) |  |  |  |  |  |  |  |  |  |  |  |  |
| Summer 2 PD experience |  |  |  |  |  |  |  |  |  |  |  |  |
| Teachers implement intervention |  |  |  |  |  |  |  |  |  |  |  |  |
| Ongoing PD for teachers |  |  |  |  |  |  |  |  |  |  |  |  |
| Collect and analyze teacher data |  |  |  |  |  |  |  |  |  |  |  |  |
| Collect and analyze student data |  |  |  |  |  |  |  |  |  |  |  |  |
| Revision of intervention and PD experience |  |  |  |  |  |  |  |  |  |  |  |  |
| Formative feedback from advisory board |  |  |  |  |  |  |  |  |  |  |  |  |
| Summative project evaluation (E&A Center) |  |  |  |  |  |  |  |  |  |  |  |  |